## Sheet1
TASK TITLE | START DATE | DUE DATE
|  |  | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
PHASE 1: PLANNING
REVIEW PROJECT REQUEST | 05/27/2025 | 2025-02-06 | bar: MAY to JUN
PRIORITIZE PROJECT REQUEST | 05/27/2025 | 2025-03-06 | bar: MAY to JUN
ALLOCATE RESOURCES | 05/27/2025 | 2025-03-06 | bar: MAY to JUN
IDENTIFY PROJECT DEVELOPMENT TEAM | 05/27/2025 | 2025-02-06 | bar: MAY to JUN
FINALIZING PROPOSED TITLE AND SYSTEM | 05/27/2025 | 05/31/2025 | bar: MAY
DOCUMENTATION | 05/27/2025 | ONGOING | bar: MAY to JUN
PHASE 2: ANALYSIS
DOCUMENTATION | 05/27/2025 | ONGOING | bar: JUL to AUG
CONDUCT PRELIMINARY INVESTIGATION | 2025-03-06 | 2025-06-06 | bar: JUN
STUDY CURRENT SYSTEM | 2025-03-06 | 07/14/2025 | bar: JUN to JUL
DETERMINE USER REQUIREMENTS | 2025-03-06 | 06/13/2025 | bar: JUN
PHASE 3: DESIGN
DOCUMENTATION | 05/27/2025 | ONGOING | bar: SEP to NOV
HARDWARE USED | 06/16/2025 | 06/17/2025 | bar: JUN
SOFTWARE USED | 06/16/2025 | 06/23/2025 | bar: JUN
DEVELOP DETAILS OF THE SYSTEM | 06/23/2025 | ONGOING | bar: JUN to AUG
DEPLOYMENT OF THE SYSTEM | 2025-01-08 | ONGOING | bar: AUG
PHASE 4: IMPLEMENTATION
DEVELOP PROGRAM |  | ONGOING
INSTALL AND TEST NEW SYSTEM